## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to AI compliance checker and LLMs, compliance in GDPR and HIPAA jurisdiction | MUST HAVE | No Dependency | Yakshi Rami | 3- Completed
S1 | S1 | US-001 | Automatic identification of the key clauses in contracts | MUST HAVE | Contract Database dependent | Yakshi Rami | 3- Completed
S2 | S2 | US-001 | Continuously monitor legal databases for changes | MUST HAVE | Contract Dataset | Yakshi Rami | 3- Completed
S2 | S2 | US-001 | Suggest modifications to contracts based on detected risks | MUST HAVE | Based on LLM and Transformer | Yakshi Rami | 3- Completed
S3 | S3 | US-001 | LLM to generate suggested amendment language for high-risk clauses, based on the specific regulatory standard | MUST HAVE | Based on LLM and Transformer | Yakshi Rami | 3- Completed
S3 | S3 | US-001 | System to trigger an email notification immediately when a newly uploaded contract receives a "High" risk score | MUST HAVE | Based on LLM and Transformer | Yakshi Rami | 3- Completed
S4 | S4 | US-001 | Structured JSON to generate a professional, formatted PDF report summarizing the compliance check | MUST HAVE | structured JSON output | Yakshi Rami | 3- Completed
S4 | S4 | US-001 | End-to-end process tested (upload, check, recommend, notify) to confirm the system meets all compliance outcomes | MUST HAVE | Entire Contract | Yakshi Rami | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 55 | 15 | 9 | 9 | 7 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to AI compliance checker and LLMs, compliance in GDPR and HIPAA jurisdiction | 2025-09-18 | 2025-09-20 | Yakshi Rami | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Automatic identification of the key clauses in contracts | 2025-09-19 | 2025-09-21 | Yakshi Rami | Coding | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Continuously monitor legal databases for changes | 2025-09-20 | 2025-09-22 | Yakshi Rami | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Suggest modifications to contracts based on detected risks | 2025-09-21 | 2025-09-23 | Yakshi Rami | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | LLM to generate suggested amendment language for high-risk clauses, based on the specific regulatory standard | 2025-09-22 | 2025-09-24 | Yakshi Rami | Build | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | System to trigger an email notification immediately when a newly uploaded contract receives a "High" risk score | 2025-09-23 | 2025-09-25 | Yakshi Rami | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Structured JSON to generate a professional, formatted PDF report summarizing the compliance check | 2025-09-24 | 2025-09-26 | Yakshi Rami | Coding | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | End-to-end process tested (upload, check, recommend, notify) to confirm the system meets all compliance outcomes | 2025-09-25 | 2025-09-27 | Yakshi Rami | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | The PDF parsing library is failing to correctly handle tables and formatting in scanned documents. | Investigated alternative libraries and scheduled a test comparison
Sprint 1 | Day 4 | Setting up the local LLM environment (LangChain) is delayed due to network restrictions on downloading necessary dependencies. | Switched to using the hosted OpenAI/Groq API key for initial development
Sprint 2 | Day 6 | The public website scraping logic for regulatory updates is occasionally blocked by the target site's anti-bot measures. | Implemented header rotation and delayed polling strategy
Sprint 3 | Day 7 | The LLM-generated suggested amendments in JSON format are sometimes malformed, causing parsing issues in the modification module. | Added a "retry with prompt refinement" logic to the LLM call; implemented schema validation before passing the output to the modification module.
Sprint 4 | Day 9 | Integration testing with the client's internal Slack workspace is stalled awaiting approval for the custom app permissions. | Shifted focus to finalizing the PDF report generation and UI polish until permissions are granted.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-18 | 2025-09-27 | Yakshi Rami | Documenting complex technical decisions (e.g., NLP choice) | Spending excessive time troubleshooting dependency conflicts | Daily 15-minute pairing sessions for code reviews | Standardize a single Docker image for development environment setup
2 | Sprint 2 | 2025-09-28 | 2025-10-12 | Yakshi Rami | Creating short, focused training data sets for the LLM to understand context-specific terminology. | Providing unstructured feedback on extracted clauses | Proactively flagging potential regulatory ambiguity early | Implement a structured feedback form for clause validation
3 | Sprint 3 | 2025-10-13 | 2025-10-27 | Yakshi,Masthan,Dharani,Rajakarthikeyan | Holding a dedicated "Integration Prep" before starting a new platform integration | Rushing the unit tests for data scraping logic, leading to intermittent failures later. | Using the new structured feedback form to improve the Clause Identification model | Allocate 1.5x original estimate for unit testing all data input/output components
4 | sprint 4 | 2025-10-28 | 2025-11-11 | Yakshi,Masthan,Dharani,Rajakarthikeyan | Breaking down large user stories into smaller, clearer technical tasks during the sprint planning meeting | Allowing scope creep in the risk scoring feature after the sprint started. | Maintaining clear communication on API changes across modules | Strictly enforce "no new scope during the sprint" policy